## Sheet1
Tasks | Duration (Hours)
GUI | 3
Login Screen | 2
Manager Account | 1
Firebase | 5
Vehicle Creation | 1
Garage Generation | 2 | MONDAY 4/15 | TUESDAY 4/16 | THURSDAY 4/18 | SATURDAY 4/20
Ticket Generation | 1
Reciept Generation | 2 | FIREBASE | FINISH LOGIN | VEHICLE GEN | TICKET AND RECIEPT GEN
Javadoc | 1 | LOGINSCREEN | MANAGER ACC | GARAGE GEN | JAVADOC
Junit Testing | 1 |  | REGISTER ACC |  | FINISH GUI
UML Class Diagram | 1
SUM of Hours | 20